## Full List_V2
Scenario/ Theme | Project Risks and Mitigation Strategies. | Env & Dev Methodology, Impact on Work Streams | Comprehensive Test Strategy, Mitigate risks | Customer Project Governance | Environment Management | Source Control and CI/CD Release Management | Line6 | Line7 | Line8
Universal Properties | UP would like to pilot the application to the UK-based offices first in the next 6 months and release it to the other regions after. Each region may have region-specific requirements that need to be defined. UP would like guidance on which development methodology to use. | UP has geographically separated IT teams responsible for the 4 CRM system, website, and billing systems. The CRM teams, in particular, have operated with a great deal of autonomy. | Historically, UP finds that bugs that were fixed in UAT still show up in Production. Given the limited bandwidth for the testing team, they do their best to manually test all their use cases after deployment in both UAT and Prod environments. UP would like recommendations on how to prevent these from occurring. | Both the new CRM platform and the external portal have to support English, German and French and Spanish based on the user's language. | The IT teams have access to only one development and one test environment for each of their respective systems.
Universal Parcel | UPL would like to outsource the custom development to one of the consulting companies, so the high resource turnover can be expected. | UPL would like to engage with a design agency to design the UI for the customer's mobile app. The app should be available from day one in Apple Store and Google Store. |  | The IT Department raised concerns about a size of the backlog of potential tasks, but without clear priorities nor details required to start development. | UPL had in the past an incident with leaks of customers' data, which probably were extracted from their UAT org. They are looking for recommendations on how to prevent this kind of situation.
UPL would like recommendations on how to increase system adoption, manage changes developed by local Administrators and avoid hitting Salesforce limits due to country-specific changes
Green House Recycling | GRC would like recommendations on how to manage the project to address project priorities, technical design issues, team management, and organizational issues that may arise. | GRC has six separate teams (across the US, Canada, and India) responsible for the two ERP systems and the four logistics systems. The logistics teams in particular have operated with a great deal of autonomy and with no central guidance on technical standards. | While some source code is shared, all testing and deployment is currently manual. This has led to several incidents impacting the ability of the business to operate and meet regulatory requirements for systems that must be certified. | The solution needs to support English, Spanish, and French languages.
The Sales Management team at GRC would like to simultaneously release the completed solution to production for all regions in four months. However, IT would like to take a phased approach. The business is looking for guidance on the optimal plan, including on how to prioritize and track the work across the entire initiative.
Universal Safety | UST would like recommendations on how to manage the project to address project priorities, technical design issues, team management, and organizational issues that may arise. | UST has geographically separate IT teams responsible for the two ERP systems (US and Canada) and the three monitoring systems. The ERP teams in particular have operated with a great deal of autonomy. |  | The Sales Management team at UST would like to simultaneously release the completed solution to production for all regions in four months. | The IT teams have access to only one development and one test environment for each of their respective systems.
The solution needs to support both English and French languages.
Wine & Sunflowers |  | Due to the anticipated growth (and regular changes needed), Wine and Sunflowers is actively hiring for 3 development teams that will own this system going forward |  | The business has a tendency to change its mind a lot on requirements. They would like you to recommend a suitable delivery approach. |  | Releases are permitted once a month; there is an annual change freeze for all systems throughout the month of December
The management of duplicate customer records is a key requirement. There are multiple versions of the truth for customer records so they would like you to recommend a suitable solution for ensuring this customer data stays clean.
Acme Gym Equipment | In past AGET has found that requirements were missed during development and QA and need suggestion on how it can be avoided in future. | AGET has development team in China with Java experience and would like to leverage them for Salesforce development. | AGET has only 1 dev & 1 QA instances for all external system and interested to know how testing in Salesforce would be done. | System should be GDPR & PCI compliant. AGET is planning to move to new data center and hostnames may change. | Historically, AGET found that defects fixed in UAT resurface in production. They would like to understand how repeated defects can be avoided | They would like to roll out projects in one region within 4 months and the remaining region every 2 months. They are looking for a recommendation on how it can be done.
Constructus temporary Buildings | As they move into new markets, they would like to be able to rapidly enable the system to operate in these markets which will involve different languages and currencies, but which should be a common way of working. | They would like to be self-sufficient for new releases and applica/on maintenance within 12 months and would like advice on how to enable this. | How to engage users to ensure adop/on of the new system A clear understanding of what their responsibili/es would be during the project | How to minimise code errors and ensure code quality throughout the delivery
Greens & Veg |  | G&V have a small development team in Manilla who have proven themselves very effec/ve, but who do not know Salesforce at all. G&V would like advice on how to establish best practice. |  |  |  | In terms of continuous innovation, the CIO would like to commit to frequent releases and would like advice on how to achieve this with minimal issues, bugs and down/me to minimise opera/onal impact
Universal HealthBit |  | UHB’s business and IT stakeholders are located in the US. Additionally, UHB’s Java development team is based in India and may be utilized for development, testing, and support of the solution. |  | The solution must be PCI compliant. Additionally, UHB would like architectural recommendations that will enable them to grow into other global markets, the first being the EU. |  | Given the criticality of the business functions to be hosted on Salesforce UHB would like recommendations on the release approach.
Given their distributed teams and regulatory and technical constraints, UHB is seeking recommendations for the project methodology and governance structure and any recommended toolsets.
Baby Box Scenario |  | Due to high demand, the project should be run in as many parallel tracks as possible. The CEO would like to know how many workstreams are recommended. | For each workstream, the CEO would like to understand what project methodology will be used and why. The CEO would like a comprehensive testing strategy to inform her when the system is ready to go live. | The CEO would also like to establish a governance structure to manage the decisions and changes that will be occurring during the projects. The CEO would like to know what governance structures are recommended. | The CEO is also requesting an environment management plan that describes the number of unique environments, as well as a migration strategy for moving from one environment to the other.
City Scooter Share |  | CSS has multiple development teams around the world to support their operations in the 10 cities. They frequently find themselves overwriting each other’s code as they make region-specific enhancements. Management would like to understand how they can better manage their code base. | Historically, CSS finds that bugs that were fixed in UAT still show up in Production. Given the limited bandwidth for the testing team, they do their best to manually test all their use cases after deployment in both the UAT and Prod environments. CSS would like recommendations on how to prevent these from occurring. | Local support teams are not able to fix other regions’ code as each of the different development teams seem to follow their own coding standards. CSS would like be able to leverage the various support teams around the world to provide global support and is requesting recommendations to achieve this. |  | CSS would like to pilot the application to the US-based offices by the end of the year, and release to the other regions after. Each region may have region-specific requirements that need to be defined. CSS would like guidance on which development methodology to use.
Merrick Insurance |  | Each of the four policy management systems has a separate development team responsible for development on their respective systems. Members of these teams are distributed between the US, Canada, Hungary, and India. |  | The sales processes between the US and Canada are quite different, due primarily to regulatory and reporting requirements. | Currently the development teams manage their own deployments separately. However, given the criticality of coordinating the development teams for this project, MIS requires that consolidated source control, automated testing, and automated deployment be utilized.
The business and IT teams in Canada work well together, but the business and IT teams in the US have a history of conflict.
This project is viewed as an opportunity to implement best practices around the use of Salesforce, smooth coordination between project teams (both business and IT) and successful consolidation of business processes. MIS is looking for overall guidance in these areas.
Big Nasty Pharma | COVERED IN NEXT SHEET IN THIS DOCUMENT
Food Trucks R Us
Global Adventure Tours
Flower Racing
Universal Racing
UpIn Smoke | NO GOVERNANCE SECTION FOR THESE SCENARIOS
Universal Coffee Machines
Laptops 2 Schools
Clean Bikes
Hire Me Services
Musicians Incorporated
Green Roof Systems
Galaxy Cars & Trucks
Pollard Financials
Patient Travel Support
Galaxy Film Distributors
Solar Bridge INC

## Large Scenarios
Theme/Scenario | Big Nasty Pharma | Food Trucks R Us | Global Adventure Tours | Flower Racing | Universal Racing
project risks and mitigation strategies. | SVP of Clinical Research has previously been given free reign and frequently uses her large budget to complete projects “under the radar” ○ IT offshores all Salesforce development and treats the development process as a black box. Production bug count is noticeably higher than industry average | FTRUS business is rapidly changing and business wants to control and prioritize the changes that goes into the CRM application. | GAT has recently experience 2 varying outages on their website and are in the process of defining standard SLAs for all business functions. CIO (customer) has requested that Salesforce be part of this process too. | Given this involves money and charitable giving (with noted US tax authority implications), FR is committed to ensuring that those regulatory requirements are met for the pilot | Given this involves money and charitable giving (with noted US tax authority implications), UR is committed to ensuring that those regulatory requirements are met for the pilot
Project and technical governance functions to manage change and mitigate risk
FTRUS has a National Sales Meeting in coming weeks and they want to launch the CRM application in that meeting.
FTRUS IT had a recent security exposure where they lost some customer and partner data as a result of bad password policy and inadequate integration authentication. Due to this the CIO had to leave. CIO was also responsible for the application security and FTRUS is now looking for advice on how to handle the applications security going forward. FTRUS IT has now hired a new Global CIO
environment and development methodology, Impact on work streams | An appropriate methodology to manage the development of the project and ensures traceability throughout the project lifecycle | An appropriate methodology to manage the development of the project and ensures traceability throughout the project lifecycle | Due to hiring restrictions in the past, GAT relies heavily on individual contractors and System integrators. SI has not been able to control the constant churn of resources that has led to high risk/bad deliverables. GAT wants to change this approach and is open to suggestions to improve self sufficiency. | FR have developers in San Francisco who currently are accustomed to making updates manually to different environments as needed (missing code, bugs, missing reference data) through the method/tool of their choice. FR would like recommendations on whether this is best practice and optimal. | FR have developers in San Francisco who currently are accustomed to making updates manually to different environments as needed (missing code, bugs, missing reference data) through the method/tool of their choice. FR would like recommendations on whether this is best practice and optimal.
| Any idea accepted into development needs to traced all the way through deployment and reported on at any stage in the process Teams are encouraged to release every month for non­mission critical systems | 3 SI partners support FTRUS across various functions within CRM area. The development team from different vendors do development in their own lower environments and clashing defects/issues are not caught till the code is merged in UAT. This has led to bad quality and missed timelines. New CIO wants to do away with this model and wants to build a leaner development and support model. | An appropriate methodology to manage the development of the project and ensures traceability throughout the project lifecycle | A second development team is being brought onboard in Romania to work on European specific regulatory requirements. FR would like guidance on how to make the most of this new team and ensure coordinated forward project movement with the team in San Francisco. | A second development team is being brought onboard in Romania to work on European specific regulatory requirements. FR would like guidance on how to make the most of this new team and ensure coordinated forward project movement with the team in San Francisco.
comprehensive test strategy, mitigating risks | ○ A test methodology for the project that mitigates significant technical risk | FTRUS CRM QA team lacks depth and they have slow turnaround. CIO is looking to get the testing automated to remove the dependencies on QA resources and turnaround faster. | Paymentforce is a critical system for GAT and the changes to it goes through rigorous testing which itself takes multiple weeks. Even changes to any integration points in Paymentforce goes through the same testing cycles. | As DashPay serves numerous other backend systems for FR, any changes must go through rigorous testing | As DashPay serves numerous other backend systems for FR, any changes must go through rigorous testing
myTrialManager and SmartDose are heavily validated (regulated) systems and are considered mission critical. Due to changing regulations, these systems are updated 1­2 times/year and any Salesforce processes that interface with these systems needs to undergo extensive validation before release
customer project governance. | The Global CIO does not want to impinge on the flexibility of the subsidiaries and wants to keep the innovative culture across all subsidiaries | Global Food Safety VP has to be involved in the process to define food safety cases. He also engages Chief Legal Officer to follow the local regulations, in case of multiple complaints. | GAT runs its IT in 2 divisions ­ internal facing (employee) applications and external facing (customer) applications. Both the divisions are headed by respective CIO. There is also a shared services group which supports Security and PMO. Any customer facing applications also require approval from Marketing and Legal. | FR, while deeply committed to how this new technology and processes can help support goals, is more focused on racing and raising funds for charity than IT, and therefore readily admits to being disorganized. FR needs guidance on how to tackle this project in a successful manner | FR, while deeply committed to how this new technology and processes can help support goals, is more focused on racing and raising funds for charity than IT, and therefore readily admits to being disorganized. FR needs guidance on how to tackle this project in a successful manner
| Big Nasty GmbH recently hired a Global CIO who is looking to ensure that technology and development best practices are being followed across all subsidiaries as well as reduce any spending redundancies where possible especially around the tools and teams supporting the development process | FTRUS Finance has a poor track on approving any new application vendors. They have slow turnaround in case they have to approve POs for new vendors with whom FTRUS has never done business with. | Priority for CIO is to standardize the global processes and he wants to ensure that business leaders have actually signed off on these new processes before the team implements them. | FR requires that the new system is easy to use and fast for the users, as future funding and deployments depend on the success of the pilot | FR requires that the new system is easy to use and fast for the users, as future funding and deployments depend on the success of the pilot
| Project and technical governance functions to manage change and mitigate risk |  | Project and technical governance functions to manage change and mitigate risk | FR would like to debut/pilot this new system in a racing series which begins in 6 months in the US. They would like to rollout to Europe within 12 months. | FR would like to debut/pilot this new system in a racing series which begins in 6 months in the US. They would like to rollout to Europe within 12 months.
US drives a big revenue stream for GAT and IT, under pressure from US Regional Manager had to deliver US based requirements over other regions. This has caused frictions and escalations in the past.
environment management. | A deployment, release and environment strategy that includes recommendations on environments, source control and deployment techniques | POS4Truck and ERP has limited environments. And some of the defects in their legacy CRM were introduced due to not being tested in lower environments end to end. CIO wants to remove this risk and wants to know about the end to end environment plan
source control and continuous integration for release management |  | A deployment, release and environment strategy that includes recommendations on environments, source control and deployment techniques | There are separate teams for managing critical fixes vs new development. In the last quarterly release of Tour Management System, some of the Sev­1 fixes regressed during deployment of a quarterly release and has caused GAT to re­evaluate their environment and config management. GAT is seeking advice on how to manage this effectively. | FR would like a comprehensive testing, environment planning and deployment strategy based on the new system architecture | FR would like a comprehensive testing, environment planning and deployment strategy based on the new system architecture
|  | Both ERP and POS4Truck has inbuilt capabilities for configuration management and readily integrates with Subversion. FTRUS IT wants to know more about the Salesforce configuration management and how well, it can be integrated with their existing setup. | A deployment, release and environment strategy that includes recommendations on environments, source control and deployment techniques
|  | They have the similar model for their ERP changes where business gets their prioritized requirements delivered every 3 weeks.Leveraging the success of ERP development, POS4Truck is also transitioning from a quarterly changes to once a month. They have engaged ERP team to help them setup with their tools and processes. | Due to ripple impact of the changes, GAT mandates that major changes to its application are restricted to only once a quarter. Only Sev­1 and high priority Sev­2 defects are allowed as exceptions to this mandate.